## Sheet1
ID | Category | Requirement Description | Priority pack | Responsible | Estimate (Hrs) | Notes
R1 | New request form issues | Username prompt in people picker, should disappear after selection | P1 | Vendor
|  | Remove expiry date in all forms | P1 | Vendor
|  | Apply site sensitively label to the site, teams, and group | P1.2 | Vendor
|  | Remove sensitivity label option if unable to fix applying sensitivity label in this round of enhancements | P1 | Vendor
|  | Display storage quota in GB | P1 | Vendor
|  | Remove language and time zone option in request form | P1 | Vendor
|  | Transfer information icon prompts from Dev to PROD | P1 | Vendor
|  | Validate hub site URL as valid hub site | P1.2 | Vendor
|  | Ensure members and owners are unique | P1 | Vendor
|  | Display site collection admin group in information panel, during form review stage, before submission along with other approver group info. | P1 | Vendor
|  | When cloning a request, site URL does not display prefix as described in Approver Group. Please fix that. | P1 | Vendor
Add few sec delay to ensure request list is updated before redirecting user to it.
|  | Provide documentation and instructions to update information icons | P1 | Vendor
|  | Changes requested on 24th September 2024 | P1 | Vendor
1)Remove Retention policy, sensitivity label, and review date
2)Make fields mandatory
Members
3) Update information icon text to include mandatory fields
R2 | Approver Group From | Please make custom site template non mandatory | P1 | Vendor
|  | Update information icon logic to make it consistent with request form information icon | P2 | Vendor | 22 | Transfers all the information icon details to a SharePoint list for dynamic mapping during the application load.
|  | Update information icon information from DEV to PROD | P1 | Vendor
|  | Provide documentation and instructions to update information icons | P1 | Vendor
R3 | Email notifications | Update email wordings from DEV to PROD | P1 | Vendor
|  | Add site URL in approval email | P1 | Vendor
|  | Recheck to ensure emails are to going to right ppl with right wordings and sufficient information | P1 | Vendor
Changes requested on 24th September 2024
1)Approve confirmation email notification formatting changes and to include site collection administrator.
R4 | Provisioning process | Provide estimation of time it takes to provision a request | P1.2 | Vendor
|  | Fix DEV Provisioning issues | P1 | Vendor
R5 | Error Handling | Add error handling during provisioning | P1 | Vendor
Common errors found are
· user added as owner does not exist during provisioning.
· Site collection admin is format is incorrect.
· Sites trying to create have their URL reserved in purge state. They still get validated but provisioning throws error.
· Error message does not guide towards what to do next.
Document fix error and reset status process
|  | Need more information on what to do when errors are encountered. | P1 | Vendor
|  | Add error handling in power automate when provisioning fails and give meaningful response | P1 | Vendor
|  | Add error handling to deal with custom templates use | P1 | Vendor
|  | Document error troubleshooting process with clearly indication of which role can do what in what order to troubleshoot an error | P1 | Vendor
R6 | Custom Template | Provide detailed instructions on creating a custom template for SharePoint | P2 | Vendor | 16
|  | Provide detailed instructions on creating a custom template for Teams | P2 | Vendor | 16
|  | Provide detailed instructions on creating a custom template for Groups | P2 | Vendor | 16
R7 | Landing page | Reduce load time | P2 | Vendor | 18
|  | Match SharePoint templates names to that of current tool | P2 | Vendor | 4
provide instruction to rename std MS template names
R8 | Backend SharePoint site | Provide documentation for request list and other lists | P1.2 | Vendor
|  | Add multiple agency admin for a single department in same entry | P1.2 | Vendor
|  | Allow agency admin to be admin of multiple departments | P1 | Vendor
R9 | Branding | App styles and branding enhancements | P2 | Vendor | 24 | Subject to specific requirements
R10 | Hypercare and support model | Provide hypercare and | P1.2 | Vendor
Propose ongoing support model.
R11 | Script source Control | As per OCIO standard. | P1 | Vendor
R12 | Product Security assessment | For Architecture Review Group and OCIO Cyber Security approval. | P1 | Vendor, OCIO – Cyber Security
R13 | Support | Service support Matrix | P1 | OCIO - Cloud Service Operations
R14 | Support | Service Toolkit (Quick Reference Guide, Service Summary, published to Service Catalogue) | P1 | OCIO - Cloud Services Projects
R15 | Communication | Communication Plan | P1 | OCIO - Comms
R16 | Support | Governance Model | P1 | OCIO – Cloud Services
R17 | Support | Handover to Cloud Services Operations with support, error handling documentation described above | P1 | Vendor, OCIO - Cloud Services
| From the Workorder: Create and Provide Documentation and Guide for | Service Desk Application Management Tasks | P2 |  | 6
|  | Service Desk User Support Tasks and Issue Resolution | P2 |  | 6
|  | Cloud Operations Team Support and Maintenance Tasks | P2 |  | 6
|  | Cloud Operations Architecture and Configuration Documentation | P2 |  | 8